External Evaluation Report

Logging Opportunities in Online Programs for Science (LOOPS)

Dr. Barbara C. Buckley

September 30, 2008

The goals of the external evaluator, Dr. Barbara C. Buckley, in reviewing the National Science Foundation-funded LOOPS project are to evaluate project execution and fidelity to plan by providing constructive observations on project activities and findings and recommendations for future efforts.

The external evaluation efforts of this year focused on understanding project goals, progress being made toward project objectives, and the roles of the various institutions and personnel.

This report is based on data collected during the following evaluation activities:

- Review of Proposal

- Review of NSF Questions and LOOPS Answers

- Attendance at TELS retreat August 6, 2008)

- Interviews and discussions with project personnel (August 6, 208)

- Extensive discussions with Concord personnel (September 17-18, 2008)

- Review of project Wiki (http://confluence.concord.org/display/LOOPS/Home)

- Review of Web site and Portal (http://loops.concord.org/)

- Review of NSF annual report

Project Goals

LOOPS will [provide] teachers with timely formative feedback that provides insights into student learning and gives teachers instructional options that are data-driven.

Part of a long-term collaboration among the Concord Consortium, the University of California, Berkeley, the University of Toronto, and North Carolina Central University, LOOPS will create timely, valid, and actionable reports to teachers by analyzing assessments and logs of student actions generated while students use online curriculum materials. Drawing on these reports, teachers will then be able to make data-based decisions about how to best help their students learn.

LOOPS will study the effect of putting teachers in a feedback loop of data on both student and teacher learning. These feedback loops will be classroom-tested with inquiry-based materials using probes and models focused on eighth grade physical science.

In order to provide feedback to teachers, LOOPS curriculum activities will collect data on student progress—what activity each student is working on or has completed, student responses to questions, student actions as they conduct inquiry using models and probes, plus scores on various explicit assessments. LOOPS activities will calculate a few key indicators of inquiry skills in real time and present them in a format that teachers can use.

Progress toward Project Goals and Objectives

The following sections describe LOOPS project objectives and progress made toward those objectives targeted during Stage 1.

# Project Objectives

The following sections describe progress made toward these objectives as relevant to Stage 1 activities.

### Develop LOOPS technology

Significant effort has been expended on developing the infrastructure for logging student actions, analyzing their actions in real-time (based on prior work by the Modeling Across the Curriculum project (Buckley, Gobert, Horwitz, & O’Dwyer, 2008) and the TELS project (McElhaney, 2006)), and delivering reports to teachers in class as well as after class, along with other supportive resources.  The major obstacle to this effort at this point in time is an incompatibility between the existing grading tool used in the TELS project via the WISE 3.0 portal and the otml reports that display teacher reports.  This will have to be resolved in order to deliver the LOOPS Planning and Classroom Enactment Resources Version 1.0 planned for Stage 1.

### Integrate technology with existing materials

The force and motion curriculum drafted by teacher-developer Jeff Schoonover effectively incorporates existing online learning activities developed by previous projects into a coherent curriculum for force and motion with the addition of new activities designed to take advantage of the Smart Graphs feature [IS THIS TRUE?].  I do not know the current state of these activities in terms of their functionality for students or teachers.  Since most of the curriculum is based on existing activities, LOOPS integration will require not only logging student actions and responses, but also analyzing them in real time and displaying the teacher reports.  As noted above, the teacher reports are dependent on the successful resolution of the incompatibility described in the previous paragraph.

### Study inquiry learning

I DO NOT KNOW THE STATE OF THE ASSESSMENTS, RUBRICS, AND WHETHER THESE WERE PRESENTED TO THE DESIGN TEAM AT THE SUMMER RETREAT.  NOR DO I KNOW WHO IS DESIGNING THE TEACHER TRAJECTORY RESEARCH AND THE STATE OF THEIR INSTRUMENTS.

### Develop professional development strategies

Prior work by these collaborators both collectively and individually has included not only professional development but also a long history of involving teachers as developers and design partners.  For this project the focus will be on how to interpret and effectively use the data provided by the teacher reports.  In this first year teacher professional development strategies will emerge from the design partnerships with the teacher developers.  [WHO IS RESPONSIBLE FOR TEACHER PROFESSIONAL DEVELOPMENT?]

### Disseminate the materials and approach

Project materials and deliberations are already available on the project website & wiki (http://loops.concord.org/ and http://confluence.concord.org/display/LOOPS/Home.

### Stage I Baseline Assessment and LOOPS Version 1.0 (Jan 2008-Aug 2008)

Student Assessment. We will create annual assessments to track student progress and administer the assessments in all participating schools (N=1000 students). Assessments will allow us to determine impact of the instruction by week.

Knowledge Integration Rubric. We will apply the Knowledge Integration rubric (Linn et al, 2006) to the annual assessments and summarize the results for the design partnerships.

Teacher Learning. To assess the trajectory of teacher learning, we will use interviews and surveys during professional development, classroom observations, and logged student data. We will establish a baseline and refine our methods. The pilot measures will be refined and used with additional teachers in Stage IV.

Design Force and Motion, Version 1.0. To create the Force and Motion unit, LOOPS will review student learning data from the baseline assessments and all the component units to identify weekly goals and assessments. A design partnership consisting of discipline experts (Tinker & Horwitz), technology experts (Slotta), classroom learning experts (teachers from three schools), assessment experts (Linn, Lee, Husic), and researchers (Linn, Slotta, postdoc, graduate student) will finalize the pilot version during the summer workshop. We will use the TELS design process (Linn & Holmes, 2006) with extensive review by all stakeholders.

LOOPS Planning and Classroom Enactment Resources Version 1.0. The design partnership will finalize functional specifications for the Planning and Classroom Enactment technologies for use in Time Frames 1 and 2, during the summer workshop. The resource designs will take advantage of the annual assessment findings that indicate the impact of the traditional curriculum in the participating schools. We will design a planner and progress reports for the Force and Motion unit.

Institutional Roles

During the first year of the project there has been considerable negotiation focusing on the respective roles of the institutions involved and recruiting the personnel to carry out the work, as would be expected.  I am not totally sure that these negotiations have been concluded, but given the long history of the collaboration, I am confident that they will be.

My understanding is that Concord Consortium leads the technology development and integration efforts. Marcia Linn’s team at the University of California, Berkeley leads the research effort. Jim Slotta’s team at the University of Toronto focuses on the technology required to enhance community support for teachers. North Carolina Central University will be involved in both teacher development and research.

Conclusions

Overall, the LOOPS project is making good progress toward achieving their goals and objectives for stage 1.

Buckley, B. C., Gobert, J., Horwitz, P., & O’Dwyer, L. (in revision, 2008). Looking inside the black box: Assessing model-based learning and inquiry in BioLogica. International Journal of Learning Technologies.

McElhaney, K. W. (2006). Connecting students’ learning gains to the sophistication of their experiments with a dynamic, interactive visualization. Unpublished manuscript. University of California, Berkeley.