Logging Opportunities in Online Programs for Science (LOOPS): Student and Teacher Learning

Annual Report 2008

# Participants

Many participants contributed to the LOOPS project during the first year of the project.  The primary team from Concord Consortium includes:

Robert Tinker, PI, oversees all aspects of the scientific and educational quality of the project.

Paul Horwitz, co-PI, is a Senior Scientist working on curriculum design and reporting strategies

Ken Bell, Project Director, supports the entire project team with planning and scheduling of the various project meetings and collaborations

Stephen Bannasch, Director of Technology, is responsible for the underlying project architecture.

Scott Cytacki, senior software engineer, supervises the development of software for the project

Aaron Unger, junior programmer, works on OTrunk models, Reporting, and the supporting SAIL/OTrunk frameworks.

Others from CC who have participated in the project this year are: junior programmers Sam Fentress and Seong June Kim, curriculum developer Carolyn Staudt, Paul Burney CC webmaster, Ben Greslick CC system administrator and Cynthia McIntyre Director of Communications at CC.

The primary LOOPS leadership team from UC Berkeley includes: Marcia Linn (co-PI Director), Kathy Benemann (Project Manager), Doug Kirkpatrick (Program Coordinator). Graduate students include Kevin McElhaney, Helen Zhang, Phil Daubenmeir, and Jenny Chiu. Technology staff includes Hiroki Terashima, Geeff Kwan, and Tony Perritano. Additional staff includes David Crowell and Jon Breitbart.

University of Toronto Ontario Institute of Science Education participants include: Jim Slotta, co-PI and the Director of the LOOPS project at the University of Toronto. Rokham Sadeghnezhadfard, David Leung and Ali Ajellu technology developers, Cheryl Madeira and Naxin Zhao PhD student researchers.

Partner schools  and Teachers

Glenbrook MS, Mt. Diablo USD:  Concord CA Mike Marshall

Valley View MS, Mt. Diablo USD: Pleasant Hill, California  Matt Hesby

Martinez JHS, Martinez USD: Lauren Norse & Jefferson Hartman

Albany MS, Albany USD: Eric Mapes & Marty Place

Other collaborators or contacts

Consultants – Jeffrey Schoonover Curriculum Developer, Barbara Buckley Project Evaluator

# Activities

The goal of the

LOOPS project is to use the cyber infrastructure to provide resources that support inquiry in the middle school science classroom. The project will make innovative use of technology to create timely, valid, and actionable reports to teachers by analyzing assessments and logs of student actions generated in the course of using online curriculum materials. These reports will enable teachers to make data-based decisions concerning alternative teaching strategies.

The project is a collaboration of the Concord Consortium with a research group at the University of California, Berkeley, and another group located at the University of Toronto. In order to coordinate the efforts of these remotely-situated teams, during the first year of the project we organized [how many?] face-to-face meetings, at Concord and at the other two locations [note: is this true?] and have held conference calls every two weeks. Below, we report on the activities of each participating team separately.

[List dates and locations of face-to-face meetings.]

Activities at the Concord Consortium.

In addition to its responsibility for the overall management of the project, the Concord Consortium’s main role has been to design and implement the infrastructure technology required to make it a success. In accomplishing this goal, we have adapted and enhanced the SAIL (Scalable Archictecture for Interactive Learning) [ref] technology developed by the TELS Center on a previous NSF grant [give NSF project number and dates of performance]. NSF GRANT #  ESI0334199  October 2003 to August 2008  Paul Horwitz PI

The Concord Consortium has also played an important role in curriculum development, based on the California 8th grade science standards for the two curricular strands of the project: Force and Motion, and Chemical Reactions.

Development of Technological Infrastructure 

Installation.

What have we done to make installation easier for schools? (If nothing, leave this out.)

Curriculum tools

Describe the development of Smart Graphs, Smart Tables, and Smart Models and their use within LOOPS. Any other curriculum tools that LOOPS can justifiably claim credit for?

Authoring

Goal: to enable curriculum developers who are not programmers to author LOOPS activities. Describe the authoring system in its current state, and how it is supported by OTrunk, SDS, and whatever other infrastructure technology. Give a specific example of an authored activity (e.g., the motion probe one) to point out how easy it is to author these.

Information management

A central feature of LOOPS is the persistence of student data and the use of such data by the classroom teacher. Describe the technologies we are creating so that data generated as students use our technology can be used creatively by teachers both during and after class. Describe the new features of the LOOPS Teacher Dashboard (e.g., managing groups of students) that the SAIL portal doesn’t have, thus justifying our development of a second portal. Provide brief description of the process of portal development in JRuby and the advantages of JRuby over Java for that purpose.

Reporting

Describe and give examples of LOOPS reports, emphasizing their advantages over previous versions, including tracking teacher-initiated changes, real-time reporting of student work, grouping of students, and support for performance assessment rubrics.

University of California, Berkeley activities

The UC Berkeley sub award for the LOOPS project was executed in 2008. Leadership includes Marcia Linn (Director) and Kathy Benemann (Manager), Doug Kirkpatrick (Program Coordinator). Graduate students include Kevin McElhaney, Helen Zhang, Phil Daubenmeir, and Jenny Chiu. Technology staff includes Hiroki Terashima, Geeff Kwan, and Tony Perritano. Staff includes David Crowell and Jon Breitbart. The Berkeley Institutional Review Board has accepted UC Berkeley's LOOPS protocol.

UC Berkeley participants have contributed to a face-to-face meeting in Concord and regular technology and leaders meetings (averaging three times a month). In addition, Bell and Benemann have coordinated on a weekly basis. In addition, we have contributed to the WIKI for LOOPS.

During the first year we have reviewed and pilot tested possible items for baseline assessments, recruited teachers and schools, began the process of defining LOOPS scenarios, and conducted meetings with potential LOOPS users. In addition, we have reviewed possible curriculum and technology designs and considered ways to incorporate LOOPS.

Assessment

Baseline assessments for Force and Motion and Chemical Reactions items were administered to both TELS and non-TELS students based on convenience. The two groups are not comparable as they come from schools with different Academic Performance Index scores. These are all items that have been released by TIMSS or other testing programs.

The pilot tests can be used to establish goals for the new curriculum materials. As the bar chart below shows, performance on Force and Motion items suggests a need for intervention in student learning in this topic area (Figure 1).  For schools that did not study TELS, this can be seen as a baseline. As is apparent, students have limited understanding of the topics in these assessments.

INSERT FIGURE 1 here

Figure One: Five items administered to students in TELS schools who either did or did not study any TELS units the previous year.

The Chemical Reactions items were administered to students in similar schools. An analysis of Chemical Reactions items indicates significant advantage to students who experienced TELS instruction consistent with the impact of the unit in the past (Figure 2).

INSERT FIGURE 2 here

Figure Two: Seven items administered to students of two TELS teachers.

LOOPS Schools

UC Berkeley has recruited three schools to participate in the LOOPS project and one school to participate as a potential back-up school. All of these schools have participated in past TELS-related research programs and have garnered administrative and district-level support for integrating effective use of technology into science curriculum. Several formal and informal meetings have been organized since June 2008, during which we collaborated with teachers and researchers in the curriculum and technology design process.

We secured pacing guides for physical science courses. We have reviewed these guides as well as the California standards. Since this is the first year of use of the guides we envision some revision after the plan is tried out. The timing of the units and the time devoted to topics appears a bit disjointed. To make LOOPS successful we will need to align the guides with our curriculum design plan.

Our first formal meeting in July provided us with invaluable insight into teacher's successes and challenges when teaching Force and Motion topics to middle school students. Most of the teachers expressed excitement about their prior use of motion probes and indicated interest in continuing to use this technology. The teachers were somewhat confused about the goals of LOOPS and how the program would be enacted in their classrooms. In response we began the process of creating scenarios.

During our second formal meeting in August, attended also by Concord Consortium project manager Ken Bell, we were able to gather teacher perspectives into revising current TELS modules to fit LOOPS research and instructional goals, while also evaluating new technology tools. Kevin McElhaney, who has been serving as the LOOPS graduate student researcher, played an essential role during these planning meetings, providing both teachers and senior researchers avenues for designing activities and the accompanying technology components.

These meetings underscored the importance of clarifying LOOPS scenarios and developing proof of concept technologies. These materials will be discussed with teachers as they become available.

LOOPS Scenarios

We have participated in the iterative process of drafting LOOPS scenarios. These discussions are helping us identify the kinds of feedback systems that might be desirable in the classroom setting. UC Berkeley, Concord Consortium, and Toronto have revised these scenarios. We will soon discuss these ideas with teachers and further refine the scenarios.

We have discussed various curriculum approaches, recently meeting with Tinker at Berkeley to refine the context of instruction and consider appropriate pacing arrangements.

University of Toronto activities

Continued development of the Scalable Architecture for Interactive Learning (SAIL).

Since 2003, Professor Slotta has led an international team of researchers and technology designers in developing SAIL, which is a java-based framework for the development of interactive, interoperable learning materials and environments.  SAIL has been the basis of our development activity in the NSF-funded TELS center, and is one of the primary deliverables of that effort.  It has served as the basis of all technology development in subsequent projects, including LOOPS

Organized a SAIL technology architecture workshop.  June 23, 2008.  Utrecht, The Netherlands

Professor Slotta organized, with collaborator Turadg Aleahmad and Stephen Bannasch, a pre-conference workshop where members of the international community were exposed to the core LOOPS technologies and encouraged to design new applications that would connect to their own research.  15 participants gathered in Utrecht, the Netherlands, including representatives from a large European Union Framework 7 project called SCY that is interested in collaborating in technology development, as well as members of prestigious U.S. and Scandinavian labs.  This workshop was a full day event, with participants first exploring SAIL and LOOPS technologies, then breaking into focus groups (one on technology architectures and repositories, and another on curriculum and assessments).

Convened a SAIL repository development workshop.  August 1-5, 2008.  Berkeley, California.

Building on the earlier technology workshop, Professor Slotta invited the two lead technology developers from the SCY (Science Created by You) project to participate in a hands-on development workshop held in Berkeley, California.  SCY is a large collaboration project funded by the European Union's Framework 7 program (8.5 Million Euros from 2008-2013).  Professor Slotta is a partner in this project, as he is eligible being from a Canadian institution.  Slotta is a primary member of the SCY technology architecture and pedagogical agents work packages.  To ensure that SAIL is of direct relevance to SCY, Slotta convened a workshop where the two lead programmers from SCY joined the three lead programmers from the TELS center and two programmers from his group at University of Toronto, to develop a new  Repository Of Open source Learning Objects (ROOLO) that would interconnect with the existing SAIL portal that all three groups were using. This repository was successfully developed and is now being used in all three locations, with Slotta's team in Toronto taking a lead role.

LOOPS technology development meeting.  August 5-8, 2008. Berkeley, California

In conjunction with the fifth (and final) annual TELS retreat, Slotta led a break-out session of the various members of the TELS and LOOPS technology teams to discuss issues and agendas for technology development (for which Slotta has overall responsibility).  Several major topics were discussed, including authoring, reporting, portals, and repositories.  A SAIL technology retreat was planned where these topics would be more fully discussed, to be held in mid October, in Ontario, Canada.

Ongoing leadership and research meetings.

Professor Slotta has joined regular meetings of the LOOPS leaders where research and technology development is planned.  He also convened a weekly technology development meeting, where other members of his technology group participated.  Finally, Slotta and two PhD students, Cheryl Madeira and Naxin Zhao, attended bi-monthly meetings of the LOOPS research community.

# Publications & Products

University of Toronto Publications

Krajcik, J., Slotta, J.D., McNeil, K. and Reiser, B. (2008). Designing Learning Environments to Support Students’ Students Constructing Integrated Understanding.  In Y. Kali, M. C. Linn, & J. E. Roseman (Eds.), Designing Coherent Science Education. New York: Teachers College Press.

Slotta, J.D. and Peters, V. (2008). A Blended Model for Knowledge Communities:  Embedding Scaffolded Inquiry. Proceedings of the International Conference of the Learning Sciences.  Utrecht.

Peters, V. and Slotta, J.D. (2008). Building Wiki-Based Pedagogical Scripts for Knowledge Communities. Proceedings of the International Conference of the Learning Sciences.  Utrecht.

Slotta, J. D. (in press). Evolving the classrooms of the future: The interplay of pedagogy, technology and community.  To appear in Mäkitalo-Siegl, K., Kaplan, F., Zottmann, J. & Fischer, F. (Eds.). Classroom of the Future. Orchestrating collaborative spaces. Rotterdam: Sense.

Slotta, J. D. & Jorde, D. (in press). Learning from our peers in international exchanges:  When is worth doing, and how can we help it succeed?  The International Journal of Science Education.

Workshops

Slotta, J.D., Aleahmad, T., and Bannasch, S. (2008). The Scalable Architecture for Interactive Learning (SAIL) - New tools and communities for research. Workshop presentation at the International Conference of the Learning Sciences (ICLS).  Utrecht, The Netherlands

Conference Presentations:

Najafi, H., Slotta, J. D. & Gelb, D. (2008, August). Promoting knowledge building in graduate-level education: Opportunities and pitfalls . Paper presented at the IKIT Summer Institute, Toronto, ON.

Peters, V., & Slotta, J. D. (2008). Building wiki-based pedagogical scripts for knowledge communities. Proceedings of the International Conference of the Learning Sciences. June 23-27.  Utrecht, The Netherlands.

Slotta, J.D. and Peters, V. (2008). A Blended Model for Knowledge Communities: Embedding Scaffolded Inquiry. Paper presented at the bi-annual meeting of the International Conference of the Learning Sciences (ICLS).  June 23-27.  Utrecht, The Netherlands.

Peters, V., & Slotta, J.D. (2008). Co-designing wiki-based scripts for secondary school biology. Paper presented at the annual meeting of the Canadian Society for Studies in Education. May 31 – June 3. Vancouver, BC.

Najafi, H., Slotta, J., Gelb, D. (2008). Understanding the relationships between curriculum planning decisions, patterns of activity, and learning outcomes: An analysis of the evolution of a course community. Paper presented at the annual meeting of the Canadian Society for the Study of Education. May 31 – June 3. Vancouver, BC.

Peters, V., & Slotta, J. D. (2008). Connecting Knowledge Building With Scripted Activities in a Secondary School Biology Classroom: A Case Study. Paper presented at the annual meeting of the American Educational Research Association, New York, NY.

Concord Consortium Publications

Bannasch, S., & Tinker, R. (2008). A Brief Description of the SAIL Environment (Monograph). Concord, MA: The Concord Consortium.

Levy, D., & Tinker, R. (2008). Links between dynamic representations of atomic-scale phenomena and molecular reasoning Paper presented at the Chais Conference on Instructional Technologies Research.

Tinker, R. (2007). How do students learn from models? Case studies in guided inquiry. @Concord, 11(1), 14-15.

Tinker, R. (2007). How technology will revolutionize STEM learning. Paper presented at the NESDEC Annual Meeting.

Tinker, R. (2007). Learning and Technology: Expanding Opportunities. Paper presented at the National Value of Science Education Conference.

Tinker, R. (2007). Potholes in the road to proving technology. @Concord, 11(1), 2-5.

Tinker, R. (2007). The Educational Accelerator: A virtual facility for educational R&D. Paper presented at the Enabling science discoveries through visual exploration.

Tinker, R. (2008). Exploring the Science of Atoms and Molecules Using the Molecular Workbench. Paper presented at the AAPT Annual Winter Meeting.

Tinker, R. (2008). Learning What Students Are Thinking Paper presented at the AAPT Winter Meeting.

Tinker, R. (2008). Perspective: The Concord Consorium vision. @Concord, 12(1), 2-3.

Tinker, R., & Bell, K. (2008). The Center for Enhanced Learning of Science. @Concord, 12(1), 10-11.

Tinker, R., & Staudt, C. (2008). The Molecular Workbench: Linking the Micro and Macro. Paper presented at the NSTA National Conference.

Tinker, R., & Staudt, C. (2008). The Science of Atoms and Molecules. Paper presented at the NSTA National Conference.

Tinker, R., Staudt, C., & Hazzard, E. (2008). Probes and Models in the High School. Paper presented at the NSTA National Conference.

Tinker, R., & Xie, Q. (2008). Applying computational science to education: the Molecular Workbench paradigm. Computing in Science and Engineering, 10(5), 24-27.

Tinker, R., & Xie, Q. (Invited for 2009). Infusing Science into Science Education. Science.

Tinker, R., Xie, Q., O'Brian, E., & Pallant, A. (2007). Chemistry visualization and student learning: Light-matter interactions using Molecular Workbench models. Paper presented at the AERA Annual Meeting.

Zucker, A., Galvis, A. H., & Tinker, R. (2007). Probeware and the XO. @Concord, 11(1), 1, 4-5.

NEED Berkeley and Concord Publications Workshops and Presentations

Add Barbara Buckley material ?